## Sheet1
UI Design | Resource | Web Pages | Effort (hrs) | Functionality | Effort (hrs) | Section | Effort (hrs)
Login page | ZY | 2 | 4 | User Management |  | UI Design | 222
Sign Up Page | ZY | 1 | 4 | User Sign Up | 8 | Functionality | 279
Home page | KS | 1 | 16 | View User List (Admin) *Member Point | 16 | Total Hours | 501
User Management Page (Admin) | KS | 2 | 16 | Edit User
User Profile Page (Include Member Point) | KS | 2 | 4 | Delete User
Password Reset Page | KS | 1 | 8 | Add Staff | 8
Password Changing Page | KS | 1 | 4 | View Staff List
Product Management Page | ZY | 1 | 16 | Edit Staff
Product Editing Page (Depends to PMP) | ZY | 1 | 8 | Delete Staff
Product List Page (Browsing View) | ZY | 1 | 8 | Login | 4
Product Detailed Page | ZY | 1 | 8 | Logout
Payment Checkout Page | JX | 1 | 16 | Change Password | 22
Receipt Page | JX | 1 | 8 | User Verification
Order History Page (Admin & User) | JX | 2 | 16 | Forgot Password (Reset)
Order Details Page | JX | 1 | 8 | Product Management
Payment Record Page (Admin) | JX | 1 | 16 | Add Unlimited Product | 35
Cart List | JX | 1 | 14 | Edit Product Info
Dashboard | KS | 1 | 40 | Delete Product
Feedback Form & WhatsApp | ZY | 1 | 8 | View Product List
Total |  | 23 | 222 | Delist Product
|  |  |  | Filter Product | 8
Search Product
|  |  |  | Discount (Bundle Price + Customize Discount) | 32
Inventory Management
|  |  |  | Stock In (Admin/Staff) | 4
Stock Out (All)
|  |  |  | Filter Inventory (Brand/Expiry Date/Batch/Serial Number) *On hold | ?
|  |  |  | Stock Low Alert (Email Notification) | 8
Payment Management
|  |  |  | Accumulate Member Point | 8
Discount with Member Point
|  |  |  | Email Receipt/Download Receipt | 8
|  |  |  | Payment Gateway Integration | 16
Order Management
|  |  |  | View Order Record | 8
|  |  |  | Checkout (Check stock balance) | 12
|  |  |  | View Order Detail (Staff/Use confirm order) | 8
|  |  |  | Create/Cancel Order (renew stock balance) | 8
|  |  |  | CIUD Delivery Location (main & aternative location) | 8
|  |  |  | Update order delivery status (confirm/delivery pending) | 2
Cart Management
|  |  |  | Add to Cart | 16
Remove from Cart
Modify Item Amount
Check stock balance
Dashboard Monitoring
|  |  |  | Sales Reporting (Monthly/specific time frame or last 30 days) | 8
|  |  |  | Order Reporting (Pie Chart by product in last 3 months) | 8
|  |  |  | Delivery Reporting (Numbering) | 8
Inventory Reporting (Pie Chart by low stock)
Membership Point Reporting (Pie Chart By Point in range)
|  |  |  | Download Transaction Report (For audit) | 8
Contact
|  |  |  | Feedback Form | 8
WhatsApp Integration
|  |  |  | Total | 279

## Duration Estimation
UI Design | User Type | Resource | Web Pages | Effort (hrs) | Functionality | Effort (hrs) | Section | Effort (hrs)
Login page | Admin/Staff/User | ZY | 3 | 4 | User Management |  | UI Design | 248
Sign Up Page | Admin/Staff/User | ZY | 1 | 4 | User Sign Up | 8 | Functionality | 267
Home page | User | KS | 1 | 16 | View User List (Admin) *Member Point | 16 | Total Hours | 515
User Management Page (Admin) | Admin | KS | 3 | 16 | Edit User
User Profile Page (Include Member Point) | Admin/Staff/User | KS | 3 | 4 | Delete User
Password Reset Page (Admin/User) | Admin/User | KS | 2 | 8 | Add Staff | 8
Password Changing Page (Admin/User) | Admin/User | KS | 2 | 4 | View Staff List
Product Management Page | Admin/Staff | ZY | 2 | 16 | Edit Staff
Product Adding & Editing Page (Depends to PMP) | Admin/Staff | ZY | 4 | 8 | Delete Staff
Product Browsing Page | User | ZY | 1 | 8 | Login | 4
Product Detailed Page (User) | User | ZY | 1 | 8 | Logout
Payment Checkout Page | User | JX | 1 | 16 | Change Password | 22
Location Selecting Page | User | JX | 2 | 11 | User Verification
Receipt Page | User | JX | 1 | 8 | Forgot Password (Reset)
Order History Page (Admin/Staff/User) | Admin/Staff/User | JX | 3 | 16 | Product Management
Order Details Page (Admin/Staff/User) | Admin/Staff/User | JX | 3 | 8 | Add Unlimited Product | 35
Payment Record Page (Admin/Staff) | Admin/Staff | JX | 2 | 16 | Edit Product Info
Cart Page | User | JX | 1 | 14 | Delete Product
Dashboard | Admin | KS | 1 | 40 | View Product List
Feedback Form & WhatsApp Button | User | ZY | 1 | 8 | Delist Product
Inventory Management Page (List/Create/Edit) | Admin/Staff | KS | 6 | 15 | Search Product | 8
Total | 3 | 3 | 44 | 248 | Generate ready message and direct to WhatsApp (car model & battery model) | 8
Inventory Management
| zy - 56 |  |  |  | Inventory (CRUD) | 15
| ks - 103 |  |  |  | Stock Low Alert (Email Notification) | 8
| jx - 89 |  |  |  | Payment Management
[5 empty] | Accumulate Member Point | 8
Discount with Member Point
[5 empty] | Email Receipt/Download Receipt | 8
[5 empty] | Payment Gateway Integration | 16
[5 empty] | Voucher Discount | 3
Order Management
[5 empty] | View Order Record | 24
View Order Detail (Staff/Use confirm order)
Create Order
Update Order (renew stock balance)
[5 empty] | Select & Change Delivery Location (locate location) | 8
[5 empty] | Checkout before payment (Check stock balance) | 12
Cart Management
[5 empty] | Add to Cart | 16
Remove from Cart
Modify Item Amount
Check stock balance and provide the total price
Dashboard Monitoring
[5 empty] | Sales Reporting (Monthly/specific time frame or last 30 days) | 8
[5 empty] | Order Reporting (Pie Chart by product in last 3 months) | 8
[5 empty] | Delivery Reporting (Numbering) | 8
Inventory Reporting (Pie Chart by low stock)
Membership Point Reporting (Pie Chart By Point in range)
[5 empty] | Download Transaction Report (For audit) | 8
Contact
[5 empty] | Feedback Form | 8
WhatsApp Integration
[5 empty] | Total | 267

## Duration Estimation_v2
UI Design | User Type | Resource | Web Pages | Effort (hrs) | Functionality | Effort (hrs) | Section | Effort (hrs)
Login page | Admin/Staff/User | ZY | 3 | 4 | User Management |  | UI Design | 252
Sign Up Page | Admin/Staff/User | ZY | 1 | 4 | User Sign Up | 8 | Functionality | 268
Home page | User | KS | 1 | 16 | View User List (Admin) *Member Point | 16 | Total Hours | 520
User Management Page | Admin | KS | 3 | 16 | Edit User
User Profile Page (Include Member Point) | Admin/Staff/User | JX | 3 | 4 | Delete User
Password Reset Page | Admin/User | JX | 2 | 8 | Add Staff | 8
Password Changing Page | Admin/User | JX | 2 | 4 | View Staff List
Product Management Page | Admin/Staff | ZY | 2 | 16 | Edit Staff
Product Browsing Page | User | ZY | 1 | 8 | Delete Staff
Product Detailed Page | User | ZY | 1 | 8 | Login | 4
Warranty Page | User | KS | 1 | 2 | Logout
Payment Checkout Page | User | JX | 1 | 16 | Change Password | 22
Location Selecting Page | User | JX | 2 | 12 | User Verification
Receipt Page | User | ZY | 1 | 8 | Forgot Password (Reset)
Order History Page | User | JX | 1 | 16 | Product Management
Order Details Page | User | JX | 1 | 8 | Add Unlimited Product | 35
Order Management Page | Admin/Staff | JX | 2 | 16 | Edit Product Info
Payment Record Page | Admin/Staff | ZY | 2 | 16 | Delete Product
Cart Page | User | ZY | 1 | 14 | View Product List
Dashboard | Admin | KS | 1 | 32 | Delist Product
Feedback Form & WhatsApp Button | User | KS | 1 | 8 | Search Product | 8
Inventory Management Page (List/Create/Edit) | Admin/Staff | KS | 6 | 16 | Generate ready message and direct to WhatsApp (car model & battery model) | 8
Total | 3 | 3 | 39 | 252 | Inventory Management
[5 empty] | Inventory (CRUD) | 16
[5 empty] | Stock Low Alert (Email Notification) | 8
Payment Management
[5 empty] | Accumulate Member Point | 8
Discount with Member Point
[5 empty] | Email Receipt/Download Receipt | 8
[5 empty] | Payment Gateway Integration | 16
[5 empty] | Voucher Discount | 3
Order Management
[5 empty] | View Order Record | 24
View Order Detail (Staff/Use confirm order)
Create Order
Update Order (renew stock balance)
[5 empty] | Select & Change Delivery Location (locate location) | 8
[5 empty] | Checkout before payment (Check stock balance) | 12
Cart Management
[5 empty] | Add to Cart | 16
Remove from Cart
Modify Item Amount
Check stock balance and provide the total price
Dashboard Monitoring
[5 empty] | Sales Reporting (Monthly/specific time frame or last 30 days) | 8
[5 empty] | Order Reporting (Pie Chart by product in last 3 months) | 8
[5 empty] | Delivery Reporting (Numbering) | 8
Inventory Reporting (Pie Chart by low stock)
Membership Point Reporting (Pie Chart By Point in range)
[5 empty] | Download Transaction Report (For audit) | 8
Contact
[5 empty] | Feedback Form | 8
WhatsApp Integration
[5 empty] | Total | 268